## Cover Page
KGATELOPELE MUNICIPALITY
DRAFT SDBIP
SERVICE DELIVERY BUDGET IMPLEMENTATION PLAN
2018 / 20189

## Table of Contents
Table of Contents
1. Introduction
2. Signature of Mayor
3. Ratings for SDBIP
4. Strategic Objectives and Alignment with NKPA & KPA
5. Capex (Budget v7.2) A5
5.1 Capex (Budget v7.2) AS29
5.2 Conditional Grant (Budget v7.2) AS20
6. Revenue & Expenditure per source (A2 and A3)
6.1 Revenue Expenditure per month (SA25)
7. Revenue & Expenditure per vote
8. Organisation Structure
9. Projects IDP
10. SDBIP (Top Level)

## Introduction
The MFMA requires that municipalities prepare a Service Delivery and Budget Implementation Plan as a strategic financial management tool to ensure that budgetary decisions that are adopted by municipalities for the financial year are aligned with their Integrated Development Plan Strategy. According to section I of the Act a service delivery and budget implementation plan means a detailed plan approved by the mayor of a municipality in terms of section 53(1)(c)(ii) for implementing the municipality's delivery of municipal services and its annual budget, and which must indicate- (a) Projections for each month of the year (i) Revenue to be collected, by source; and (ii) Operational and capital expenditure, by vote; (b) Service delivery targets and performance indicators for each quarter; (c) Any other matters that may be prescribed, and includes any revisions of such plan by the mayor in terms of section 54( 1)( c); In terms of Section 53 (3) of the Municipal Finance Management Act (MFMA) No. 56 of 2003. The mayor must ensure- (a) that the revenue and expenditure projections for each month and the service delivery targets and performance indicators for each quarter, as set out in the service delivery and budget implementation plan, are made public no later than 14 days after the approval of the service delivery and budget implementation plan; and (b) that the performance agreements of the municipal manager, senior managers and any other categories of officials as may be prescribed, are made public no later than 14 days after the approval of the municipality's service delivery and budget implementation plan. Copies of such performance agreements must be submitted to the council and the MEC for local government in the province.

## Signature of Mayor
Approval of FINAL DRAFT SDBIP 2018/19
SDBIP
Date signed
Signature of Mayor
Name of Mayor

## Ratings for SDBIP
Measure for attainment
Performance not fully effective
Unacceptable Performance
Fully effective
Performance above expectations
Outstanding Performance
2
3
4
5
1

## Strategic Objectives
National KPA | Key Performance Area | Strategic objectives (SO) of the Municipality
Basic Service Delivery | Service delivery and infrastructure development | To ensure the provision of sustainable basic services to our communities
Spatial Development and Transformation | Spatial consideration | Conservation of the environment
Local Economic Development | Local economic development | To promote a conducive environment for economic development
Municipal Finance and Sustainability | Financial sustainability and viability | To ensure an effective and efficient financially viable municipality
Municipal Institutional Transformation and Development | Institutional excellence and good governance (public participation) | Democratic and accountable government.
Municipal Transformation and Organisational Development

## Capex
NC086 Kgatelopele - Table A5 Budgeted Capital Expenditure by vote, standard classification and funding
Vote Description | Ref | 2012/13 | 2013/14 | 2014/15 | Current Year 2015/16 |  |  |  | 2016/17 Medium Term Revenue & Expenditure Framework
R thousand | 1 | Audited Outcome | Audited Outcome | Audited Outcome | Original Budget | Adjusted Budget | Full Year Forecast | Pre-audit outcome | Budget Year 2016/17 | Budget Year +1 2017/18 | Budget Year +2 2018/19
Capital expenditure - Vote
Multi-year expenditure to be appropriated | 2
Vote 1 - EXECUTIVE AND COUNCIL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0
Vote 2 - MUNICIPAL MANAGER |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 3 - CORPORATE SERVICES |  | 0 | 905472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 4 - BUDGET AND TREASURY OFFICE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 5 - TECHNICAL SERVICES |  | 0 | 0 | 0 | 12707000 | 12707000 | 12707000 | 0 | 9173000 | 10120000 | 8814000
Vote 6 - COMMUNITY SERVICES |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0
Vote 7 - ECONOMIC AND ENVIRONMENT SERVICE |  | 5977248 | 5298112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 8 - TRADING SERVICE |  | 1719000 | 4765555 | 0 | 0 | 0 | 0 | 0 | 2200000 | 0 | 0
Vote 9 - [NAME OF VOTE 9] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 10 - [NAME OF VOTE 10] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 11 - [NAME OF VOTE 11] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 12 - [NAME OF VOTE 12] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 13 - [NAME OF VOTE 13] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 14 - [NAME OF VOTE 14] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 15 - [NAME OF VOTE 15] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capital multi-year expenditure sub-total | 7 | 7696248 | 10969139 | 0 | 12707000 | 12707000 | 12707000 | 0 | 12073000 | 10120000 | 8814000
Single-year expenditure to be appropriated | 2
Vote 1 - EXECUTIVE AND COUNCIL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 2 - MUNICIPAL MANAGER |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 3 - CORPORATE SERVICES |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 4 - BUDGET AND TREASURY OFFICE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 5 - TECHNICAL SERVICES |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 6 - COMMUNITY SERVICES |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 7 - ECONOMIC AND ENVIRONMENT SERVICE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 8 - TRADING SERVICE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 9 - [NAME OF VOTE 9] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 10 - [NAME OF VOTE 10] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 11 - [NAME OF VOTE 11] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 12 - [NAME OF VOTE 12] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 13 - [NAME OF VOTE 13] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 14 - [NAME OF VOTE 14] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 15 - [NAME OF VOTE 15] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capital single-year expenditure sub-total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Capital Expenditure - Vote |  | 7696248 | 10969139 | 0 | 12707000 | 12707000 | 12707000 | 0 | 12073000 | 10120000 | 8814000
Capital Expenditure - Standard
Governance and administration |  | 0 | 905472 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0
Executive and council | [8 empty] | 500000
Budget and treasury office
Corporate services |  | 0 | 905472
Community and public safety |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0
Community and social services |  | 0 | 0
Sport and recreation
Public safety | [8 empty] | 200000
Housing |  |  |  | 0
Health
Economic and environmental services |  | 5977248 | 5298112 | 0 | 2100000 | 2100000 | 2100000 | 0 | 0 | 0 | 0
Planning and development |  |  |  |  | 0 | 0 | 0
Road transport |  | 5977248 | 5298112 |  | 2100000 | 2100000 | 2100000
Environmental protection |  |  |  |  | 0 | 0 | 0
Trading services |  | 1719000 | 4765555 | 0 | 10607000 | 10607000 | 10607000 | 0 | 11373000 | 10120000 | 8814000
Electricity |  | 69000 |  | 0 | 1500000 | 1500000 | 1500000 |  | 2700000 | 2000000 | 500000
Water |  | 44000 | 4041323 | 0 | 8916000 | 8916000 | 8916000 |  | 7673000 | 8120000 | 8314000
Waste water management |  | 165000 | 724232 | 0 | 191000 | 191000 | 191000 |  | 1000000
Waste management |  | 1441000 |  | 0 | 0 | 0 | 0
Other |  |  |  |  | 0 | 0 | 0
Total Capital Expenditure - Standard | 3 | 7696248 | 10969139 | 0 | 12707000 | 12707000 | 12707000 | 0 | 12073000 | 10120000 | 8814000
Funded by:
National Government |  | 7696248 | 10969139 | 0 | 7931000 | 7931000 | 7931000 |  | 9173000 | 10120000 | 8814000
Provincial Government |  |  |  | 0 | 4776000 | 4776000 | 4776000
District Municipality |  |  |  |  | 0 | 0 | 0
Other transfers and grants |  | 0 |  |  | 0 | 0 | 0
Transfers recognised - capital | 4 | 7696248 | 10969139 | 0 | 12707000 | 12707000 | 12707000 | 0 | 9173000 | 10120000 | 8814000
Public contributions & donations | 5 |  | 0
Borrowing | 6 |  |  | 0
Internally generated funds | [8 empty] | 2900000
Total Capital Funding | 7 | 7696248 | 10969139 | 0 | 12707000 | 12707000 | 12707000 | 0 | 12073000 | 10120000 | 8814000

## Rev. Exp per source and vote
NC086 Kgatelopele - Table A3 Budgeted Financial Performance (revenue and expenditure by municipal vote)
Vote Description | Ref | 2012/13 | 2013/14 | 2014/15 | Current Year 2015/16 |  |  | 2016/17 Medium Term Revenue & Expenditure Framework
R thousand |  | Audited Outcome | Audited Outcome | Audited Outcome | Original Budget | Adjusted Budget | Full Year Forecast | Budget Year 2016/17 | Budget Year +1 2017/18 | Budget Year +2 2018/19
Revenue by Vote | 1
Vote 1 - EXECUTIVE AND COUNCIL |  | 0 | 0 | 0 | 10218000 | 10218000 | 10218000 | 22464000 | 23416000 | 23810000
Vote 2 - MUNICIPAL MANAGER |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 3 - CORPORATE SERVICES |  | 0 | 0 | 0 | 23071000 | 23071000 | 23071000 | 11461948 | 12172722.776 | 12890945.4198
Vote 4 - BUDGET AND TREASURY OFFICE |  | 0 | 0 | 0 | 2721000 | 2721000 | 2721000 | 3144000 | 3338928 | 3535924.752
Vote 5 - TECHNICAL SERVICES |  | 0 | 0 | 0 | 39354000 | 39354000 | 39354000 | 0 | 0 | 0
Vote 6 - COMMUNITY SERVICES |  | 0 | 0 | 0 | 0 | 0 | 0 | 98000 | 104000 | 110000
Vote 7 - ECONOMIC AND ENVIRONMENT SERVICE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 8 - TRADING SERVICE |  | 0 | 0 | 0 | 0 | 0 | 0 | 40996000 | 43537000 | 46106000
Vote 9 - [NAME OF VOTE 9] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 10 - [NAME OF VOTE 10] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 11 - [NAME OF VOTE 11] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 12 - [NAME OF VOTE 12] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 13 - [NAME OF VOTE 13] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 14 - [NAME OF VOTE 14] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 15 - [NAME OF VOTE 15] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue by Vote | 2 | 0 | 0 | 0 | 75364000 | 75364000 | 75364000 | 78163948 | 82568650.776 | 86452870.1718
Expenditure by Vote to be appropriated | 1
Vote 1 - EXECUTIVE AND COUNCIL |  | 0 | 0 | 0 | 3231000 | 3231000 | 3231000 | 7076000 | 7514712 | 7958080.008
Vote 2 - MUNICIPAL MANAGER |  | 0 | 0 | 0 | 0 | 0 | 0 | 6796000 | 7217352 | 7643175.768
Vote 3 - CORPORATE SERVICES |  | 0 | 0 | 0 | 8056000 | 8056000 | 8056000 | 5736000 | 6091632 | 6451038.288
Vote 4 - BUDGET AND TREASURY OFFICE |  | 0 | 0 | 0 | 12726000 | 12726000 | 12726000 | 14269000 | 14712678 | 15580726.002
Vote 5 - TECHNICAL SERVICES |  | 0 | 0 | 0 | 51351000 | 51351000 | 51351000 | 44237000 | 46978694 | 48763436.946
Vote 6 - COMMUNITY SERVICES |  | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 53100 | 56232.9
Vote 7 - ECONOMIC AND ENVIRONMENT SERVICE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 8 - TRADING SERVICE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 9 - [NAME OF VOTE 9] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 10 - [NAME OF VOTE 10] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 11 - [NAME OF VOTE 11] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 12 - [NAME OF VOTE 12] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 13 - [NAME OF VOTE 13] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 14 - [NAME OF VOTE 14] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 15 - [NAME OF VOTE 15] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expenditure by Vote | 2 | 0 | 0 | 0 | 75364000 | 75364000 | 75364000 | 78164000 | 82568168 | 86452689.912
Surplus/(Deficit) for the year | 2 | 0 | 0 | 0 | 0 | 0 | 0 | -52 | 482.776 | 180.2598

## IDP Projects
Vote Indicator | Total Project Value 2016/17 | Unit of Measurement | Strategic Objective | National KPA | Ward | Annual Target | Projection | Actual | Projection | Actual | Projection | Actual | Projection | Actual | Variance/Reason
KPA1 | R6,500,000 |  | To ensure the provision of sustainable basic services to the community. | Basic Service Delivery | ALL | Refurbishment of Water Service Infrastructure phase 4 by 30 June 2019 | 25% implementation of project by 30 September 2018 |  | 50% implementation of the project by 31 December 2018 |  | 75% implementation of project by 31 March 2019 |  | 100% implementation of project by 30 June 2019
KPA1 | R11 165 501 |  | To ensure the provision of sustainable basic services to the community. | Basic Service Delivery | ALL | Upgrading of the existing sewage purification works by 30 December 2018 | 25% implementation of project by 30 September 2018 |  | 50% implementation of the project by 31 December 2018 |  | N/A |  | N/A
KPA1 | 75000 |  | To ensure the provision of sustainable basic services to the community. | Basic Service Delivery | ALL | Numbering of cemeteries by 30 June 2019 | 25% implementation of project by 30 September 2018 |  | 50% implementation of the project by 31 December 2018 |  | 75% implementation of project by 31 March 2019 |  | 100% implementation of project by 30 June 2019
KPA1 | 508023 |  |  | Basic Service Delivery | ALL | Conversion of 122 Indigent conventional water meters to pre-paid water meters by 30 June 2019 | 25% implementation of project by 30 September 2018 |  | 50% implementation of the project by 31 December 2018 |  | 75% implementation of project by 31 March 2019 |  | 100% implementation of project by 30 June 2019
KPA1 | R1 820 000 |  | To ensure the provision of sustainable basic services to the community. | Basic Service Delivery | ALL | Replacement of 60 electrical poles by 30 June 2019 | 25% implementation of project by 30 September 2018 |  | 50% implementation of the project by 31 December 2018 |  | 75% implementation of project by 31 March 2019 |  | 100% implementation of project by 30 June 2019
KPA1 | 6700000 |  | To ensure the provision of sustainable basic services to the community. | Basic Service Delivery | ALL | Upgrading and Refurbishment of the existing Electrical Main Sub-station by 30 June 2019 | 25% implementation of project by 30 September 2018 |  | 50% implementation of the project by 31 December 2018 |  | 75% implementation of project by 31 March 2019 |  | 100% implementation of project by 30 June 2019

## Top Level SDBIP
TOP LEVEL SDBIP 2018/2019
| National KPA 1: Basic Service Delivery: Service Delivery and Infrastructure Development | [10 empty] | Quarter Ending 30 Sept 2018 | Quarter Ending 31 December 2018 | Quarter Ending 31 March 2019 | Quarter Ending 30 June 2019
KPI Number | IDP Priority number | Ward | Key Focus Area | Strategic Objective | Key Performance Area | Activities / Programmes / Capital Projects | Department: Unit | KPI – Service standard | Type of Indicator | Annual Target | Vote Indicator / Budget Cost Estimation 2018/2019 | Projection | Projection | Projection | Projection
1 | 2 | ALL | Water | To ensure the provision of sustainable basic service to our communities | Basic Service Delivery | Provide clean piped water to all formal residential properties which are connected to the municipal water infrastructure network as at 30 June 2019 | Technical/Finance | sufficient water supply | Output | Provide clean piped water to formal residential properties which are connected to the municipal water infrastructure network as at 30 June 2019 | 7415188 | N/A | N/A | N/A | Provision of clean piped water to formal residential properties which are connected to the municipal water infrastructure network as at 30 June 2019
2 | 3 | ALL | Electricity | To ensure the provision of sustainable basic service to our communities | Basic Service Delivery | Provide electricity to formal residential properties connected to the municipal electrical infrastructure network for both credit and prepaid electrical metering as at 30 June 2019 | Technical/Finance | Number of formal residential properties connected to the municipal electrical infrastructure network (credit and prepaid electrical metering) | Output | Provide electricity to formal residential properties connected to the municipal electrical infrastructure network for both credit and prepaid electrical metering as at 30 June 2019 | 28966680 | N/A | N/A | N/A | Provision of electricity to formal residential properties connected to the municipal electrical infrastructure network for both credit and prepaid electrical metering as at 30 June 2019
3 | 2 | ALL | Sanitation | To ensure the provision of sustainable basic service to our communities | Basic Service Delivery | Provide sanitation services to residential properties which are connected to the municipal waste water (sanitation/sewerage) network as at 30 June 2019 | Technical/Finance | Number of residential properties which are billed for sewerage in accordance with the SAMRAS financial system | Output | Provide sanitation services to residential properties which are connected to the municipal waste water (sanitation/sewerage) network as at 30 June 2019 | 3672000 | N/A | N/A | N/A | Provision of sanitation services to residential properties which are connected to the municipal waste water (sanitation/sewerage) network as at 30 June 2019
4 | 11 | ALL | Waste Removal | To ensure the provision of sustainable basic service to our communities | Basic Service Delivery | Provision of refuse removal, refuse dumps and solid waste disposal to all residential account holders as at 30 June 2019 | Technical/Finance | Number of formal residential properties for which refuse is removed | Output | Provision of refuse removal, refuse dumps and solid waste disposal to all residential account holders as at 30 June 2019 | 5930093 | 25% of the total Number of formal residential properties for which refuse is removed by 30 September 2018 | 50% of the total Number of formal residential properties for which refuse is removed by 30 December 2018 | 75% of the total number of formal residential properties for which refuse is removed by 30 March 2019 | 100% of the total number of formal residential properties for which refuse is removed by 30 June 2019
5 | 2 | ALL | Water | To ensure the provision of sustainable basic service to our communities | Basic Service Delivery | Provide free basic water in terms of the equitable share requirements to indigent account holders by 30 June 2019 | Technical/Finance | Monthly provisioning of free basic water in terms of the equitable share requirements to indigent account holders (KL per account holders) | Ouput | Provide free basic water in terms of the equitable share requirements to indigent account holders by 30 June 2019 | 839662 | 25% Quartely provision of free basic water to an estimated number of 1500 indigent account holders by 30 September 2018 | 50% Quartely provision of free basic water to an estimated number of 1500 indigent account holders by 30 December 2018 | 75% Quarterly provision of free basic water to an estimated number of 1500 indigent account holders by 30 March 2019 | 100% Quarterly provision of free basic water to an estimated number of 1500 indigent account holders by 30 June 2019
6 | 3 | ALL | Electricity | To ensure the provision of sustainable basic service to our communities | Basic Service Delivery | Provide free basic electricity to registered indigent account holders connected to the municipal electrical infrastructure network by 30 June 2019 | Technical/Finance | Provide free basic electricity to indigent account holders in terms of the equitable share requirements measured in terms of quantum approved (Free kw basic electricity per indigent household) | Output | Provide free basic electricity to registered indigent account holders connected to the municipal electrical infrastructure network by 30 June 2019 | 936559 | 25% Quarterly provision of free basic electricity to an estimated number of 1500 indigent account holders by 30 September 2018 | 25% Quarterly provision of free basic electricity to an estimated number of 1500 indigent account holders by 31 December 2018 | 75% Quarterly provision of free basic electricity to an estimated number of 1500 indigent account holders by 31 March 2019 | 100% Quarterly provision of free basic electricity to an estimated number of 1500 indigent account holders by 30 June 2019
7 | 2 | ALL | Sanitation | To ensure the provision of sustainable basic service to our communities | Basic Service Delivery | Provide free basic sanitation services to registered indigent account holders which are connected to the municipal waste water(sanitation/sewerage)network & are billed for sewerage service,irrespective of the number of water closets(toilets) as at 30 June 2019 | Technical/Finance | 1500 Number of indigent account holders connected to the sanitation/sewerage network and are billed for sewerage services | Output | 48 number of free basic sanitation/sewerage services to an estimated number of 1500 registered indigent households network by 30 June 2019 | 2786048 | 12 Quarterly provision of free basic sanitation /sewerage to estimated 1500 indigent account holders atleast once a week by 30 September 2018 | 12 Quarterly provision of free basic sanitation /sewerage to estimated 1500 indigent account holders atleast once a week by 31 December 2018 | 12 Quarterly provision of free basic sanitation /sewerage to estimated 1500 indigent account holders atleast once a week by 31 March 2018 | 12 Quarterly provision of free basic sanitation /sewerage to estimated 1500 indigent account holders atleast once a week by 30 June 2018
8 | 11 | ALL | Waste Removal | To ensure the provision of sustainable basic service to our communities | Basic Service Delivery | Provide free basic refuse removal, refuse dumps and solid waste disposal to registered indigent account holders as at 30 June 2019 | Technical/Finance | Number of indigent account holders receiving free basic refuse removal | Output | 52 x free collection per ward of basic refuse removal, refuse dumps and solid waste disposal to registered indigent account holders as at 30 June 2019 | 2379108 | 13 Collection of waste per ward by 30 September 2018 | 13 Collection of waste per ward by 31 December 2018 | 13 Collection of waste per ward by 31 March 2019 | 13 Collection of waste per ward by 30 June 2019
9 | 2 | 1,2,3 | WATER | To ensure the provision of sustainable basic service to our communities | Basic Service Delivery | Refurbishment of Water Service Infrastructure phase 4 by 30 June 2019 | Technical Department | Efficient water supply | Output | Refurbishment of Water Service Infrastructure by phase 4 by 30 June 2019 | R6,500,000 | 25% implementation of project by 30 September 2018 | 50% implementation of the project by 31 December 2018 | 75% implementation of project by 31 March 2019 | 100% implementation of project by 30 June 2019
10 | 2 | 1,2,3 | Sanitation | To ensure the provision of sustainable basic service to our communities | Basic Service Delivery | Upgrading of the existing sewage purification works | Technical Department | Expand the Capacity of the existing oxidation ponds and improving the living standards of the residents in Kuilsville, Tlhakalatlou and Danielskuil by 31 December 2018. | Output | Upgrading of the existing sewage purification works by 30 December 2018 | R11 165 501 | 50% implementation of project by 30 September 2018 | 100% implementation of project 31 December 2018 | N/A | N/A
11 | 1 | 1,2 | Cemetery Management | To ensure the provision of sustainable basic service to our communities | Basic Service Delivery | Numbering of Cemeteries | Technical Department | Cemetery Management | Output | Numbering of cemeteries by 30 June 2019 | 85000 | 25% implementation of project by 30 September 2018 | 50% implementation of the project by 31 December 2018 | 75% implementation of project by 31 March 2019 | 100% implementation of project by 30 June 2019
12 | 11 | 3 | Solid Waste | To ensure the provision of sustainable basic service to our communities | Basic Service Delivery | Closure of Existing Landfill site and new Danielskuil Waste Site | Technical Department | Waste Management | Output | Closure of existing landfill site and establishment of new Danielskuil Waste Site by 30 June 2019 | 7975000 | 25% implementation of project by 30 September 2018 | 50% implementation of the project by 31 December 2018 | 75% implementation of project by 31 March 2019 | 100% implementation of project by 30 June 2019
13 | 3 | All | Electricity | To ensure the provision of sustainable basic service to our communities | Basic Service Delivery | Upgrading and Refurbishment of the existing Electrical Main Sub-station | Technical Department | Sufficient Electricity supply | Output | Upgrading and Refurbishment of the existing Electrical Main Sub-station by 30 June 2019 | 6700000 | 25% implementation of project by 30 September 2018 | 50% implementation of the project by 31 December 2018 | 75% implementation of project by 31 March 2019 | 100% implementation of project by 30 June 2019
14 | 3 | All | Electricity | To ensure the provision of sustainable basic service to our communities | Basic Service Delivery | Replacement of 60 electrical poles | Technical Department | Replacement of electrical poles | Output | Replacement of 60 electrical poles by 30 June 2019 | R1 820 000 | 25% implementation of project by 30 September 2018 | 50% implementation of the project by 31 December 2018 | 75% implementation of project by 31 March 2019 | 100% implementation of project by 30 June 2019
15 | 2 | All | Water and sanitation | To ensure the provision of sustainable basic service to our communities | Basic Service Delivery | Conversion of 122 Indigent conventional water meters to pre-paid water meters | Technical Department | Conversion of 122 Indigent conventional water meters to pre-paid water meters | Output | Conversion of 122 Indigent conventional water meters to pre-paid water meters by 30 June 2019 | 508023 | 25% implementation of project by 30 September 2018 | 50% implementation of the project by 31 December 2018 | 75% implementation of project by 31 March 2019 | 100% implementation of project by 30 June 2019
16 |  | All | Electrical | To ensure the provision of sustainable basic service to our communities | Basic Service Delivery | Replacement of 60 electrical poles | Technical Department | Replacement of 60 electrical poles | Output | Replacement of 60 electrical poles by 30 June 2019 | 1820000 | 25% implementation of project by 30 September 2018 | 50% implementation of the project by 31 December 2018 | 75% implementation of project by 31 March 2019 | 100% implementation of project by 30 June 2019
KPI Number | National KPA 2: Spatial Development and Transformation | [10 empty] | Quarter Ending 30 Sept 2018 | Quarter Ending 31 December 2018 | Quarter Ending 31 March 2019 | Quarter Ending 30 June 2019
| IDP Priority number | Ward | Key Focus Area | Strategic Obejctive | Key Performance Area | Activities / Programes/ Capital Projects | Department | KPI – Service standard |  | Annual Target | Vote Indicator / Budget Cost Estimation 2018/2019 | Projection | Projection | Projection | Projection
17 | 1 | All | Land | Conservation of the environment | Spatial Consideration | Review of the Land Use Management Scheme | Technical | Compliance with SPLUMA | output | Review of the Land Use Management Scheme by 30 June 2019 | 700000 | N/A | N/A | N/A | 1 Reviewed Land use management scheme by 30 June 2019
18 | 1 | All | Land Acquisition | Conservation of the environment | Spatial Consideration | Acquisition of non-dolomitic properties from the Department of Public Works | Technical | accquisition of land | output | acquisition of non-dolomitic properties from the Department of Public Works by 30 June 2019 | N/A | N/A | N/A | N/A | Acquisition of non-dolomitic properties from the Department of Public Works by 30 June 2019
19 | 1 | All | Land Management | Conservation of the environment | Spatial Consideration | Development of Informal Settlement Relocation and Upgrading Strategy and Policy | Technical | provision of sustainable human settleme | output | Development of Informal Settlement Relocation and Upgrading Strategy and Policy by 30 June 2018 | 930000 | N/A | N/A | N/A | Development of Informal Settlement Relocation and Upgrading Strategy and Policy by 30 June 2018
20 | 1 | All | Land Management | Conservation of the environment | Spatial Consideration | Rectification of Stands allocations | Technical | provision of sustainable human settleme | output | Consolidation, subdivision, rezoning and conveyancing for the rectification of stands allocation by 30 June 2019 | 200000 | N/A | N/A | N/A | Consolidation, subdivision, rezoning and conveyancing for the rectification of stands allocation by 30 June 2019
21 | 11 | ALL | Recycling of waste Material | Conservation of the environment | Spatial Consideration | Facilitate one recycling activity by 30 June 2019. | Technical and community services | Promoting the collection of waste | output | Facilitate one recycling activity by 30 June 2019 | N/A | N/A | N/A | N/A | Facilitation of one recycling activity by 30 June 2019
KPA | National KPA 3: Local Economic Development | [10 empty] | Quarter Ending 30 Sept 2018 | Quarter Ending 31 December 2018 | Quarter Ending 31 March 2019 | Quarter Ending 30 June 2019
KPI Number | IDP Ref No. | Ward | Key Focus Area | Strategic Obejctive | KPA | Activities / Programmes / Capital Projects | Department | KPI – Service standard | Type of indicator | Annual Target | Vote Indicator / Budget Cost Estimation 2018/2019 | Projection | Projection | Projection | Projection
22 |  | ALL | Job creation | To promote a conducive environment for economic development | Economic Growth and Development | 10 temporary jobs created through projects | corporate services | Temporary jobs creation | Impact | 10 temporary jobs created through projects by 30 June 2019 | N/A | 1 Database of unemployed youth by 30 September 2018 | 50% Temporary job Created by 30 December 2018 | 75% Temporary jobs Created by 31 March 2019 | 100% Temporary Jobs Created by 30 June 2019
23 | 5 | ALL | Strategies: economic growth | To promote a conducive environment for economic development | Economic Growth and Development | Updated MoU between 3 mines | corporate services | Conclusion/Update of MoU with the mining companies | Impact | Updated MoU between thw 3 mines by 31 December 2018 | N/A | N/A | Updated MoU by 31 December 2018 | N/A | N/A
24 | 5 | ALL | Development | To promote a conducive environment for economic development | Economic Growth and Development | Review Local Economic Development Plan. | Office of the Municipal Manager | Local Economic Developement Plan | Impact | 1x Reviewed Local Economic Development plan by 30 June 2019. | N/A | N/A | N/A | N/A | 1x Reviewed Local Economic Development plan by 30 June 2019.
25 | 5 | ALL | Local Economic Development | To promote a conducive environment for economic development | Economic Growth and Development | Trading Space for SMMEs | Office of the Municipal Manager | Sustainable Economic Development | Impact | Provision of Trading space for SMMEs by 30 June 2019. | N/A | N/A | N/A | N/A | Provision of Trading space for SMMEs by 30 June 2019.
26 | 5 | ALL | Capacity building | To promote a conducive environment for economic development | Economic Growth and Development | Building Local capacity and skill development | Office of the Municipal Manager | Local contractors development | Impact | Development of 4 small local emerging suppliers through awarding contracts or sub-contracting by 30 June 2019 | N/A | 1 developed local contractor by 30 September 2018 | 1 developed local contractor by 31 december 2018 | 1 developed local contractor by 31 March 2019 | 1 developed local contractor by 30 June 2019
27 | 5 | ALL | Strategie: economic growth | To promote a conducive environment for economic development | Economic Growth and Development | Develop and update the database on municipality’s relevant economic information | Office of the Municipal Manager | SMME database development | Impact | Development of Database of all businesses by 30 June 2019 | N/A | N/A | N/A | N/A | 1 Developed Database of all businesses by 30 June 2019
28 | 5 | ALL | Tourism | To promote a conducive environment for economic development | Economic Growth and Development | Market the Municipal Area | Office of the Municipal Manager | Support one local tourism initiative | Impact | Formulation of information brochures to enhance tourism in the area by 30 June 2019 | 23000 | N/A | N/A | N/A | Formulation of information brochures to enhance tourism in the area by 30 June 2019
29 | 5 | ALL | unemployment | To promote a conducive environment for economic development | Economic Growth and Development | career opportunities | Office of the Municipal Manager | Career exhibition | Impact | 1 Career Exhibition by 30 June 2019 | N/A | N/A | N/A | N/A | 1 Career Exhibition by 30 June 2019
KPA | National KPA 4: Municipal Financial Stability | [10 empty] | Quarter Ending 30 Sept 2018 | Quarter Ending 31 December 2018 | Quarter Ending 31 March 2019 | Quarter Ending 30 June 2019
KPI Number | IDP Priority number | Ward | Key Focus Area | Strategic Obejctive | Key Performance Area | Activities / Programmes / Capital Projects | Department | KPI – Service standard | Type of Indicator | Annual Target | Vote Indicator / Budget Cost Estimation 2018/2019 | Quarterly Projections | Quarterly Projections | Quarterly Projections | Quarterly Projections
30 | 6 | ALL | Revenue enhancement | To ensure an effective and efficient financial viable municipality | Financial Sustainability | 80% Billing on operating revenue budget | Finance | Billing | Output | 80% Billing on operating revenue budget by 30 June 2019 | 48759895 | 20% Billing by 30 September 2018 | 40% billing by 31 December 2018 | 60% billing by 31 March 2019 | 80% billing by 30 June 2019
31 | 6 | ALL | Revenue Collection | To ensure an effective and efficient financial viable municipality | Financial Sustainability | 50% Collection on Billing by 30 June 2019. | Finance | Collection on Billing | Output | 50% Collection on Billing by 30 June 2019. | 24379957.5 | N/A | N/A | N/A | 50% Collection on Billing by 30 June 2019.
32 | 6 | ALL | Revenue Collection | To ensure an effective and efficient financial viable municipality | Financial Sustainability | Collection of Grant funding as per DORA allocation | Finance | Collection of Grant funding received | Output | 100% of total Capital Grant funding received by 30 June 2019 | R 15 675 000 | N/A | N/A | N/A | 100% of total Capital Grant funding received by 30 June 2019
33 | 6 | ALL | Revenue Collection | To ensure an effective and efficient financial viable municipality | Financial Sustainability | Collection of Grant funding as per DORA allocation | Finance | Collection of Conditional Grants | Output | 100% Collection of Conditional Grants by 30 June 2019 | 23549000 | N/A | N/A | N/A | 100% Collection of Conditional Grants by 30 June 2019
34 | 6 | ALL | Revenue Planned | To ensure an effective and efficient financial viable municipality | Financial Sustainability | Indigent registration | Finance | Number of Indigent Households registered | Output | Update the indigent household registered by 30 June 2019 | N/A | N/A | N/A | N/A | Updated number of indigent household registered by 30 June 2019
35 | 6 | ALL | Asset Acquisition | To ensure an effective and efficient financial viable municipality | Financial Sustainability | Purchasing of Technical Department Vehicle | Finance | 1x Technical Deaprtment vehicle | Output | 1x Technical Department Vehicle purchased by 30 June 2019 | 400000 | N/A | N/A | N/A | 1x Technical Department Vehicle purchased by 30 June 2019
36 | 6 | ALL | Asset Acquisition | To ensure an effective and efficient financial viable municipality | Financial Sustainability | Purchasing of Council Vehicle | Finance | 1x Council Vehicle | Output | 1x Council Vehicle by 30 June 2019 | 500000 | N/A | N/A | N/A | 1x Council Vehicle by 30 June 2019
37 | 6 | ALL | Budget Expenditure | To ensure an effective and efficient financial viable municipality | Financial Sustainability | Capital Budget Expenditure | Finance | 100% of Capital Budget Expenditure | Output | 100% of Capital Budget Expenditure by 30 June 2019 | R 15 675 000 | 25% of Capital spent by 30 September 2018 | 50% of Capital spent by 31`December 2018 | 75% of Capital spent by 31 March 2019 | 100% of Capital spent by 30 June 2019
38 | 6 | ALL | Cost containment | To ensure an effective and efficient financial viable municipality | Financial Sustainability | 75% Percentage of operating budget expenditure spent. | Finance | Spend operating budget expenditure as per approved budget. | Output | 75% of operating budget expenditure spent by 30 June 2019 | 72989266 | 18.75% of operating budget expenditure spent by 30 September 2018 | 18.75% of operating budget expenditure spent by 31 December 2018 | 18.75% of operating budget expenditure spent by 31 March 2019 | 18.75% of operating budget expenditure spent by 30 June 2019
39 | 6 | ALL | Asset management | To ensure an effective and efficient financial viable municipality | Financial Sustainability | Compilation a GRAP compliant asset register by 31 August 2018 | Finance | GRAP compliant asset register | Output | GRAP compliant asset register by 31 August 2018 | 667900 | GRAP compliant asset register.31 August 2018 | N/A | N/A | N/A
41 | 6 | ALL | Asset management | To ensure an effective and efficient financial viable municipality | Financial Sustainability | 4 Quarterly Update of Asset Register by 30 June 2019 | Finance | Update of Asset Register | Output | 4 Quarterly Updates of the Asset Register by 30 June 2019 | N/A | 1 Quarterly Update of Asset Register by 30 September 2018 | 1 Quarterly Update of Asset Register by 31 December 2018 | 1 Quarterly Update of Asset Register by 31 March 2019 | 1 Quarterly Update of Asset Register by 30 June 2019
42 | 6 | ALL | Asset management | To ensure an effective and efficient financial viable municipality | Financial Sustainability | 4 quarterly undertaking of stores by 30 June 2019 | Finance | undertakings of inventory of stores | Output | 4 quarterly undertakings of inventory of stores by 30 June 2019 | N/A | 1 quarterly undertaking of inventory of stores by 30 September 2018 | 1 quarterly undertaking of inventory of stores by 31 December 2018 | 1 quarterly undertaking of inventory of stores by 31 March 2019 | 1 quarterly undertaking of inventory of stores by 30 June 2019
43 | 6 | ALL | Asset management | To ensure an effective and efficient financial viable municipality | Financial Sustainability | Report on list of assests that need to be disposed by 31 January 2019 | Finance | Disposal of assets | Output | Report on list of Assets that need to be disposed by 31 January 2019 | N/A | N/A | N/A | Report on list of assests that need to be disposed by 31 January 2019 | N/A
44 | 6 | ALL | Supply Chain Management | To ensure an effective and efficient financial viable municipality | Financial Sustainability | Disclose in AFS all monthly reported deviations condoned by Council by 31 August 2018 | Finance | Monthly reported deviations condoned by Council | Output | 1 XDisclosure note in AFS by 31 August 2018 | N/A | 1 X Disclosure note in AFS by 31 August 2018 | N/A | N/A | N/A
45 | 6 | ALL | Supply Chain Management | To ensure an effective and efficient financial viable municipality | Financial Sustainability | Formulating of procurement plan by 30 June 2018 | Finance | Formulation of procurement plan | Output | 1x Procurement plan by 30 June 2018 | N/A | Formulating of procurement plan by 30 June 2018 | N/A | N/A | N/A
46 | 6 | ALL | Supply Chain Management | To ensure an effective and efficient financial viable municipality | Financial Sustainability | 100% Compliance with the procurement plan by 30 June 2019 | Finance: Supply Chain | compliance with procurement plan | Output | 100% Compliance with the procurement plan by 30 June 2019 | N/A | 25% Implementation of Procurement Plan by 30 September 2018 | 50% Implementation of Procurement Plan by 31 December 2018 | 75% Implementation of Procurement Plan by 31 March 2019 | 100% Implementation of Procurement Plan by 30 June 2019
47 | 6 | ALL | Financial reporting | To ensure an effective and efficient financial viable municipality | Financial Sustainability | Compilation of biannual GRAP compliant Financial Statements by 30 June 2019 | Finance: Supply Chain | compilation of Annual Financial Statements | Output | Compilation of biannual GRAP compliant Financial Statements by 30 June 2019 | N/A | N/A | N/A | N/A | Compilation of biannual GRAP compliant Financial Statements by 30 June 2019
48 | 6 | ALL | Financial reporting | To ensure an effective and efficient financial viable municipality | Financial Sustainability | Compilation of biannual GRAP compliant Financial Statements by 30 June 2019 | Finance | Annual Financial Statements | Output | Compilation of GRAP compliant Annual Financial Statements by 31 August 2018 | R1 474 200 | 1 AFS per annum submited by 31 August 31 2018 | N/A | N/A | N/A
49 | 6 | ALL | Budgeting | To ensure an effective and efficient financial viable municipality | Financial Sustainability | Submission of Draft Budget to Council for approval by 31 March 2019 | Finance | Submission of Draft Budget | Output | Submission of Draft Budget to Council for approval by 31 March 2019 | N/A | N/A | N/A | Submission of Draft Budget 31 March 2019 | N/A
50 | 6 | ALL | Budgeting | To ensure an effective and efficient financial viable municipality | Financial Sustainability | Submission of Final Budget to Council for approval by 31 May 2018 | Finance | Submission of Final Budget | Output | Submission of Final Budget by 31 May 2019 | N/A | N/A | N/A | N/A | Submit the Final Budget to Council for approval by 31 May 2019
51 | 6 | ALL | Budget Funding | To ensure an effective and efficient financial viable municipality | Financial Sustainability | Submission of Adjustment budget to Council for approval by 25 January 2019 | Finance | Adjustment budget | Output | 1 X Adjusted budget per annum by 25 January 2019 | N/A | N/A | N/A | 1 X Adjusted budget by 25 January 2019 | N/A
52 | 6 | ALL | Budgeting | To ensure an effective and efficient financial viable municipality | Financial Sustainability | Review of SDBIP by 25 January 2018 | Finance | Reviewed SDBIP | Output | Reviewed SDBIP by 25 January 2019 | N/A | Reviewed SDBIP by 25 January 2019 | N/A | N/A | N/A
53 | 6 | ALL | Reporting Requirements | To ensure an effective and efficient financial viable municipality | Financial Sustainability | Submission of Monthly Section 71 reports to the Mayor and Treasury 10 working days after the end of each month by 15 July 2019 | Finance to MM/Mayor | Reporting to Treasury | Output | 12 monthly Section 71 Reports submitted to the Mayor and Treasury by 15 July 2019 | N/A | 3X Section 71 Reports submitted by 10 October 2018 | 3 X Section 71 Reports submitted by 10 January 2018 | 3X Section 71 Reports subbmitted by 10 April 2019 | 3X Section 71 Reports submitted by 10 July 2019
54 | 6 | ALL | Reporting Requirements | To ensure an effective and efficient financial viable municipality | Financial Sustainability | 4x Section 52 reports submitted quarterly to Council for approval and then submitted to Treasury by 31 July 2019 | Finance to Council | Section 52 report submitted quarterly | Output | 4x Section 52 reports submitted quarterly to Council for approval and then submitted to Treasury by 31 July 2019 | N/A | Section 52 report submitted by end of 31 October 2018 | Section 52 report submitted by 31 Januray 2018 | Section 52 report submitted by 31 April 2019 | Section 52 report submitted by 31 July 2019
55 | 6 | ALL | Reporting Requirements | To ensure an effective and efficient financial viable municipality | Financial Sustainability | Section 72 Report submitted once a year for approval by Council and then to Treasury by 25 January 2018 | Finance to Council | Section 72 Report submitted once a year | Output | Section 72 Report submitted once a year for approval by Council and then to Treasury by 25 January 2018 | N/A | N/A | N/A | 1x Section72 Report submitted by 25 Jan 2019 | N/A
KPA | National KPA 5: Municipal Institutional Transformation and development | [10 empty] | Quarter Ending 30 Sept 2018 | Quarter Ending 31 December 2018 | Quarter Ending 31 March 2019 | Quarter Ending 30 June 2019
KPI Number | IDP Priority number | Ward | Key Focus Area | Strategic Objective | Key Performance Area | Activities / Programmes & Capital Projects | Department | KPI – Service standard |  | Annual Target | Vote Indicator / Budget Cost Estimation 2018/2019 | Quarterly Projections | Quarterly Projections | Quarterly Projections | Quarterly Projections
56 | 6 | ALL | Organisational structure | Democratic and accountable government, Municipal Transformation and Organisational development | Institutional Transformation | Filling in of key vacancies | Corporate Services | Capacity Building | Output | 100 % Appointment of Council Officer, Risk Officer, Billing Officer, Creditors Officer, Assets Officer, Senior Admin, 2 Care Takers, 1 electrician, 8 General Workers and 1 driver for sanitation unit, Project Technician, 8 General Workers for waste unit by 30 June 20019 | 4475953 | 25% Appointments on budgeted vacancies by 30 September 2018 | 50% Appointments on budgeted vacancies by 31 December 2018 | 75% Appointments on budgeted vacancies by 31 March 2019 | 100% Appointments on budgeted vacancies by 30 June 2018
57 | 6 | ALL | Organisational structure | Democratic and accountable government, Municipal Transformation and Organisational development | Institutional Transformation | Formulation of job descriptions for new posts created. | Corporate Services | Job descriptions | Output | Formulation of job descriptions for new posts by 31 July 2018 | N/A | 100% Fomulated job descriptions by 31 July 2018 | N/A | N/A | N/A
58 | 6 |  | Organisational structure | Democratic and accountable government, Municipal Transformation and Organisational development | Institutional Transformation | Development/Review of Employment Equity Plan | Corporate Services | Development/Review of an employment equity plan | Output | Development/Review of an employment equity plan by 31 August 2018 | N/A | Development/Review of an employment equity plan by 31 August 2018 | N/A | N/A | N/A
59 | 6 | ALL | Human capital and skills development | Democratic and accountable government, Municipal Transformation and Organisational development | Institutional Transformation | Functionality of training committee through sitting of 6 training committee meetings by 30 June 2019 | Corporate Services | Functionality of training committee | Output | 6 training committee meetings by 30 June 2019 | N/A | 2 training committee meetings by 30 September 2018 | 1 training committee meeting by 31 December 2018 | 2 training committee meetings by 31 March 2019 | 1 training committee meeting by 30 June 2019
60 | 6 | ALL | Human capital and skills development | Democratic and accountable government, Municipal Transformation and Organisational development | Institutional Transformation | Development of a Workskills Plan by 30 April 2019 | Corporate Services | Development of Workskills Plan | Output | Development of a Workskills Plan by 30 April 2019 | N/A | N/A | N/A | N/A | 100% Developed Workskills plan by 30 April 2019
62 | 61 | ALL | Human capital and skills development | Democratic and accountable government, Municipal Transformation and Organisational development | Institutional Transformation | Compliance with the implementation of the workskills plan through 92% expenditure of workskills plan | Corporate Services | Actual budget spent on the implementation of the workplace skills plan | Output | 92% of the allocated worskills plan budget to be spent by 30 June 2019 | 838822 | 23% of the allocated worskills plan budget to be spent by 30 September 2018 | 46% of the allocated worskills plan budget to be spent by 31 December 2018 | 69% of the allocated worskills plan budget to be spent by 31 March 2019 | 92% of the allocated worskills plan budget to be spent by 30 June 2019
62 | 6 | ALL | Human resources management | Democratic and accountable government, Municipal Transformation and Organisational development | Institutional Transformation | Functionality of LLF Committee through 4 quarterly sittings of LLF meetings by 30 June 2019 | Corporate Services | Meeting of the LLF | Output | 4 quarterly LLF meetings by 30 June 2019 | N/A | 1 LLF meeting by 30 September 2018 | 1 LLF meeting by 31 December 2018 | 1 LLF meeting by 31 March 2019 | 1 LLF meeting by 30 June 2019
63 | 6 | ALL | Human resources management | Democratic and accountable government, Municipal Transformation and Organisational development | Institutional Transformation | 80% resolution of labour disputes by 30 June 2019 | Corporate Services | Resolution on all labour disputes | Output | 80% resolution of labour disputes by 30 June 2019 | N/A | N/A | N/A | N/A | 80% resolution of labour disputes by 30 June 2019
64 | 6 | ALL | Human resources management | Democratic and accountable government, Municipal Transformation and Organisational development | Institutional Transformation | Percentage % induction of newly appointed of staff by 30 November 2018 | Corporate Services | Induction of newly appointed staff | Output | 100% of all newly appointed staff inducted by 30 November 2018 | N/A | N/A | 100% of all newly appointed staff inducted by 30 November 2018 | N/A | N/A
65 | 6 | ALL | Human resources management | Democratic and accountable government,Municipal Transformation and Organisational development | Institutional Transformation | Evaluation of newly established posts and updating of existing posts for re-evaluation | Corporate Services | Evaluation of newly established posts and updating of existing for re-evaluation by 31 January 2019 | Output | Evaluation of newly established posts and updating of existing posts for re-evaluation by 31 January 2019 | N/A | N/A | Evaluation of newly established posts and updating of existing posts for re-evaluation by 31 January 2019 | N/A | N/A
66 | 6 | ALL | Human resources management | Democratic and accountable government,Municipal Transformation and Organisational development | Institutional Transformation | 4 quarterly health and safety meetings by 30 June 2019 | Corporate Service | Health and Safety | Output | 4 quarterly health and safety meetings by 30 June 2019 | N/A | 1 Health and Safety Committe meeting held by 30 September 2018 | 1 Health and Safety Committe meeting held by 31 December 2018 | 1 Health and Safety Committe meeting held by 31 March 2019 | 1 Health and Safety Committe meeting held by 30 June 2019
67 | 6 | ALL | Human resources management | Democratic and accountable government, Municipal Transformation and Organisational development | Institutional Transformation | Sitting of 3 staff meetings by 30 June 2019 | Office of the Municipal Manager | Sitting of staff meetings | Output | 4 staff meetings held by 30 June 2019 | N/A | 1 staff meeting held by 30 September 2016 | 1 staff meeting held by 31 December 2018 | 1 staff meeting held by 31 March 2017 | 1 staff meeting held by 30 June 2017
68 | 6 | ALL | Human resources management | Democratic and accountable government, Municipal Transformation and Organisational development | Institutional Transformation | 4 quarterly sitting of extended management meeting by 30 June 2019 | Office of the Municipal Manager | Quarterly sitting of extended management meeting | Output | 4 quarterly sitting of extended management meeting by 30 June 2019 | N/A | 1 sitting of extended management meeting by 30 September 2018 | 1 sitting of extended management meeting by 31 December 2018 | 1 sitting of extended management meeting by 31 March 2019 | 1 sitting of extended management meeting by 30 June 2019
69 | 6 | ALL | Performance management | Democratic and accountable government, Municipal Transformation and Organisational development | Institutional Transformation | Formulation of all section 56 and 57 Managers’ performance plans by 01 July 2018 | Office of the Municipal Manager | Formulation of performance plans | Output | Formulation of all section 56 and 57 Managers’ performance plans by 01 July 2018 | N/A | fomulated performance plans by of 01 July 2018 | N/A | N/A | N/A
70 | 6 | ALL | Performance management | Democratic and accountable government, Municipal Transformation and Organisational development | Institutional Transformation | Tabling of mid-year s72 report for approval by Council by 25 January 2019 | Office of the Municipal Manager | Mid-year s72 report | Output | 1 mid-year S72 report submitted to Council by 25 January 2019 | N/A | N/A | N/A | 1 S72 report per annum by 25 January 2019 | N/A
71 | 6 | ALL | Performance management | Democratic and accountable government, Municipal Transformation and Organisational development | Institutional Transformation | 4 Quarterly Performance Assessments by 31 July 2019 | Office of the Municipal Manager | No of performance assessment conducted | Output | 1x Quarterly=4x performance assessments by 31 July 2019 | N/A | 1 Quarterly Performance Assessments by 15 October 2018 | 1 Quarterly Performance Assessment by 15 January 2019 | 1 Quarterly Performance Assessment by 15 April 2019 | 1 Quarterly Performance Assessment by 15 July 2019
72 | 6 | ALL | Systems and technology | Democratic and accountable government, Municipal Transformation and Organisational development | Institutional Transformation | ICT governance structure | Corporate services | Improve the ICT Governance structure | Output | 4 meetings of IT Committee by 30 June 2019 | N/A | 1 Quarterly sitting of IT Comittee by 30 September 2018 | 1 Quarterly sitting of IT Comittee by 31 December 2018 | 1 Quarterly sitting of IT Comittee by 31 March 2019 | 1 Quarterly sitting of IT Comittee by 30 June 2019
KPA | National KPA 6: Good Governance | [10 empty] | Quarter Ending 30 Sept 2018 | Quarter Ending 31 December 2018 | Quarter Ending 31 March 2019 | Quarter Ending 30 June 2019
KPI Number | IDP Priority Number | Wards | Key Focus Area | Strategic Objective | Key Performance Area | Activities / Programmes / Capital Projects | Department | KPI – Service standard |  | Annual Target | Vote Indicator / Budget Cost Estimation 2018/2019 | Projection | Projection | Projection | Projection
73 | 6 | ALL | Governance structures | Democratic and accountable government | Good Governance | 4 x Quarterly Council meetings held by 31 July 2019 | Corporate Services | Number of Council meetings | Output | 4 x Quarterly Council meetings held by 31 July 2019 | N/A | 1X Council meetings held by 31 October 2018 | 1x Council meeting held by 31 January 2018 | 1x Council meeting held by 31 April 2019 | 1x Council meeting held by 30 July 2019
74 | 6 | ALL | Governance structures | Democratic and accountable government | Good Governance | 10 Special Council Meetings by 30 June 2019 | Corporate Service | 10 Special Council meetings | Output | 10 Special Council Meetings by 30 June 2019 | N/A | 3 Special Council meeting by 31 August 2018 | 2 Special Councils meeting by 31 December 2018 | 3 Special Council meeting by 31 arch 2019 | 2 Special Council meeting by 30 June 2019
75 | 6 | ALL | Governnace structures | Democratic and accountable government | Good Governance | 10 Monthly sittings of Finance Comittee by 30 June 2019 | Office of the Mayor | Monthly sitting of Finance Comittee | Output | 10 Monthly sittings of Finance Committee by 30 June 2019 | N/A | 2 Monthly sittings of Finance Committee by 30 September 2018 | 3 Monthly sittings of Finance Committee by 31 December 2018 | 3 Monthly sittings of Finance Committee by 31 March 2019 | 2 Monthly sittings of Finance Committee by 30 June 2019
76 | 6 | ALL | Governnace structures | Democratic and accountable government | Good Governance | 4 Quarterly sitting of MPAC Comittee by 30 June 2019 | Office of the Mayor | Quarterly sitting of MPAC Comittee | Output | 4 Quarterly sitting of MPAC Committee by 30 June 2019 | N/A | 1 Quarterly sitting of MPAC Committee by 30 September 2018 | 1 Quarterly sitting of MPAC Committee by 31 December 2018 | 1 Quarterly sitting of MPAC Committee by 31 March 2019 | 1 Quarterly sitting of MPAC Committee by 30 June 2019
77 | 6 | ALL | Governance structures | Democratic and accountable government | Good Governance | 4 Quarterly sittings of Institutional Comittee by 30 June 2019 | Office of the Mayor | Quarterly sitting of Institutional Comittee | Output | 4 Quarterly sittings of Institutional Committee by 30 June 2019 | N/A | 1 Quarterly sitting of Institutional Committee by 30 September 2018 | 1 Quarterly sitting of Institutional Committee by 31 December 2018 | 1 Quarterly sitting of Institutional Committee by 31 March 2019 | 1 Quarterly sitting of Institutional Committee by 30 June 2019
78 | 6 | ALL | Governance structures | Democratic and accountable government | Good Governance | 10 Monthly sittings of Technical Comittee by 30 June 2019 | Office of the Mayor | Monthly sitting of Technical Comittee | Output | 10 Monthly sittings of Technical Comimttee by 30 June 2019 | N/A | 2 Monthly sittings of Technical Committee by 30 September 2018 | 3 Monthly sittings of Technical Committee by 31 December 2018 | 3 Monthly sittings of Technical Committee by 31 March 2019 | 2 Monthly sittings of Technical Committee by 30 June 2019
79 | 6 | ALL | Governance structures | Democratic and accountable government | Good Governance | 4 Quarterly sittings of Commonage Comittee by 30 June 2018 | Office of the Mayor | Quarterly sitting of Commonage Comittee | Output | 4 Quarterly sittings of Commonage Committee by 30 June 2019 | N/A | 1 Quarterly sittings of Commonage Committee by 30 September 2018 | 1 Quarterly sittings of Commonage Committee by 31 December 2018 | 1 Quarterly sittings of Commonage Committee by 31 March 2019 | 1 Quarterly sittings of Commonage Committee by 30 June 2019
80 | 6 | ALL | Governance structures: Internal Audit | Democratic and accountable government | Good Governance | 4 Quarterly sittings of Audit Committee by 30 June 2019 | Office of the Municipal Manager (Internal Audit) | Quarterly sitting of Audit committee. | Output | 4 Quarterly sittings of Audit Committee by 30 June 2019 | N/A | 1 Audit Committee meeting by 30 September 2018 | 1 Audit Committee meeting by 31 December 2018. | 1 Audit Committee meeting by 31 March 2019. | 1 Audit Committee meeting by 30 June 2019
81 | 6 | ALL | Governance structures: Internal Audit | Democratic and accountable government | Good Governance | 2 sittings of special audit committee meeting by 31 November 2018 | Office of the Municipal Manager (Internal Audit) | Sittings of special audit committee meeting by | Output | 2 sittings of special audit committee meeting by 31 November 2018 | N/A | 1 sittings of special audit committee meeting by 31 August 2018 | 1 sittings of special audit committee meeting by 31 November 2018 | N/A | N/A
82 | 6 | ALL | Internal Audit | Democratic and accountable government | Good Governance | Compilation of a risk based operational audit plan by 1 July 2018 | Office of the Municipal Manager (Internal Audit) | Risk based audit operational plan | Input | Compilation of a risk based operational audit plan by 01 July 2018 | N/A | Compilation of operational audit plan and review of strategic plan and policies by 30 June 2018 | N/A | N/A | N/A
83 | 6 | ALL | Internal Audit | Democratic and accountable government | Good Governance | Submission of reports to Management and meetings with management | Office of the Municipal Manager (Internal Audit) | Reports to Management on audits performed. | Input | Submission of finalised quarterly audit reports by 30 June 2019 | N/A | 1 x Monthly Audit report to management by 30 September 2018 | 1 x Monthly Audit report to management by 31 December 2018 | 1 x Monthly Audit report to management by 31 March 2019 | 1 x Monthly Audit report to management by 30 June 2018
84 | 6 | ALL | Internal Audit | Democratic and accountable government | Good Governance | 12 Monthly report on progress of AGSA Action Plan and recommendations made by IA by 30 June 2019 | Office of the Municipal Manager (Internal Audit) | Monthly reports on progress of AGSA Action Plan and recommendations made by IA | Output | 12 Monthly report on progress of AGSA Action Plan and recommendations made by IA by 30 June 2019 | N/A | 3 Monthly reports on progress of AGSA Action Plan and recommendations made by IA by 30 September 2018 | 3 Monthly reports on progress of AGSA Action Plan and recommendations made by IA by 31 December 2018 | 3 Monthly reports on progress of AGSA Action Plan and recommendations made by IA by 31 March 2018 | 3 Monthly reports on progress of AGSA Action Plan and recommendations made by IA by 30 June 2019
85 | 6 | ALL | Internal Audit | Democratic and accountable government | Good Governance | Completion of audits as per the operational audit plan by 30 June 2019 | Office of the Municipal Manager (Internal Audit) | Completion of audits indicated for the financial year. | Output | Completion of audits as per the operational audit plan by 30 June 2019 | N/A | 1x Audits by 30 September 2018 | Audits on Budget and Treasury department by 31 December 2018 | Audits on Corporate Services and Office of the MM departments by 31 March 2019 | Audits on Corporate Services and Office of the MM departments by 31 June 2019
86 | 6 | ALL | Risk Management | Democratic and accountable government | Good Governance | 4 quarterly Risk Assessments conducted by 30 June 2019 | Office of the Municipal Manager | Quarterly Risk Assessment conducted quarterly | Output | 4 Risk Assessments conducted by 30 June 2019 | N/A | 1 Risk Assessment conducted by 30 September 2018 | 1 Risk Assessment conducted by 31 December 2018 | 1 Risk Assessment conducted by 31 March 2019 | 1 Risk Assessment conducted by 30 June 2019
87 | 6 | ALL | Risk Management | Democratic and accountable government | Good Governance | 12 monthly reports on mitigation of risks and implementation of risk management by 30 June 2019 | Office of the Municipal Manager | Monthly Submission of Risk Management Reports | Output | 10 reports on mitigation of risks and implementation of risk management by 30 June 2019 | N/A | 2 reports on mitigation of risks and implementation of risk management by 30 September 2018 | 2 reports on mitigation of risks and implementation of risk management by 30 December 2018 | 3 reports on mitigation of risks and implementation of risk management by 30 March 2018 | 3 monthly reports on mitigation of risks and implementation of risk management by 30 June 2019
88 | 6 | ALL | Stakeholde Participation | Democratic and accountable government | Good Governance | Approval of IDP Process Plan by Council by 31 August 2018 | Office of the Municipal Manager | IDP Process Plan | Output | Approval of IDP Process Plan by Council by 31 August 2018 | N/A | 1x Aproved Process Plan by 31 August 2018 | N/A | N/A | N/A
89 | 6 | ALL | Stakeholder Partcipation | Democratic and accountable government | Good Governance | 8 (2 per ward) IDP/Budget consultative meetings by 30 June 2019 | Office of the Municipal Manager and Finance | IDP/Budget consultative meetings | Output | 8 (2 per ward) IDP/Budget consultative meetings by 30 June 2019 | N/A | 4 (1 per ward) ward based consultative meeting by 30 September 2018 | N/A | 4 (1per ward) ward based consultative meeting by 31 March 2019 | N/A
90 | 6 | ALL | Communications | Democratic and accountable government | Good Governance | 10 monthly ward commitee meetings for each ward by 30 June 2018 | Office of the Mayor | Ward committee meetings | Output | 10 monthly ward commitee meetings for each ward by 30 June 2018 | N/A | 3 ward committee meetings for each ward by 30 September 2018 | 2 ward committee meetings for each by 31 December 2018 | 3 ward committee meetings for each ward by 31 March 2019 | 2 ward committee meetings for each ward by 30 June 2019
91 | 6 | ALL | Communications | Democratic and accountable government | Good Governance | 10 monthly Ward meetings for each ward by 30 June 2018 | Office of the Municipal Manager | Ward Meetings | Output | 10 monthly Ward meetings for each ward by 30 June 2018 | N/A | 3 ward meetings for each by 30 September 2018 | 2 ward meetings for each ward by 31 December 2018 | 3 ward meetings for each ward by 31 March 2019 | 2 ward meetings for each by 30 June 2019
92 | 6 | ALL | Policies, | Democratic and accountable government | Good Governance | Approval of draft reviewed IDP by Council by 31 March 2019 | Office Of the Municipal Manager | IDP completed/reviewed and adopted | Output | 1 draft IDP approved by 31 March 2019 | N/A | N/A | N/A | 1 draft IDP approved by 31 March 2019 | N/A
93 | 6 | ALL | Policies, | Democratic and accountable government | Good Governance | Approval of final reviewed ID by Council by 31 May 2019 | Office of the Municipal Manager | IDP completed/reviewed and adopted | Output | Approval of final reviewed ID by Council by 31 May 2019 | N/A | N/A | N/A | N/A | 1 Final IDP approved by 31 May 2019
94 | 6 | ALL | IDP Committees | Democratic and accountable government | Good Governance | 4 quarterly IDP Rep Forum meetings held by 30 June 2019 | Office of the Municipal Manager | IDP Rep Forum meetings | Output | 4 quarterly IDP Rep Forum meetings held by 30 June 2019 | N/A | 1x IDP Rep Forum meetings held by 30 September 2018 | 1x IDP Rep Forum meetings held by 31 Decenber 2018 | 1x IDP Rep Forum meetings held by 31 March 2019 | 1x IDP Rep Forum meetings held by 30 June 2019
95 | 6 | ALL | IDP Committees | Democratic and accountable government | Good Governance | 4 quarterly IDP Steering Committee meetings held by 30 June 2019 | Office of the Municipal Manager | IDP Steering Committee held - Quarterly | Output | 4 quarterly IDP Steering Committee meetings held by 30 June 2019 | N/A | 1x IDP Steering Committee held 30 September 2018 | 1x IDP Steering Committee held 31 Decemebr 2018 | 1x IDP Steering Committee held 31 March 2019 | 1x IDP Steering Committee held 30 June 2019
96 | 6 | ALL | Monitor and evaluation | Democratic and accountable government | Good Governance | Submission of Draft SDBIP to Mayor for approval by 14 June 2019 | Office of the Municipal Manager | Approval of Draft SDBIP 14 days after approval of Final Budget | Output | 1 x Draft Approved SDBIP per annum by 30 June 2019 | N/A | N/A | N/A | N/A | Approval of Draft SDBIP by 14 June 2019
97 | 6 | ALL | Monitor and evaluation | Democratic and accountable government | Good Governance | Approval of Final SDBIP before Legislative deadline by 30 June 2019 | Office of the Municipal Manager | Approval of Final SDBIP before Legislative deadline | Output | Approval of Final SDBIP before Legislative deadline by 30 June 2019 | N/A | N/A | N/A | N/A | 1 x Approved Final SDBIP by 30 June 2019
98 | 6 | ALL | Monitor and evaluation | Democratic and accountable government | Good Governance | Submission of Draft Annual Report to Council by 31 August 2019 | Office of the Municipal Manager | Submission of Draft Annual Report | Output | Submission of Draft Annual Report to Council by 31 August 2019 | N/A | Submission of Draft Annual Report by 31 August 2019 | N/A | N/A | N/A
99 | 6 | ALL | Monitor and evaluation | Democratic and accountable government | Good Governance | Submission of Final Annual Report before the legislative deadline by 31 March 2019 | Office of the Municipal Manager | Submission of Final Annual Report before the legislative deadline | Output | Submission of Final Annual Report before the legislative deadline by 31 March 2019 | N/A | N/A | N/A | Submission of Final Annual Report before the legislative deadline by 31 March 2019 | N/A
100 | 6 | ALL | Customer relations | Democratic and accountable government | Good Governance | 1 x Annual Customer satisfaction assessment 30 June 2018 | Office of the Municipal Manager | Satisfaction assessment conducted | Output | 1 x Annual Customer satisfaction assessment 30 June 2018 | N/A | N/A | N/A | N/A | 1 x Annual Customer satisfaction assessment for each Ward by 30 June 2019
101 | 6 | ALL | Customer relations | Democratic and accountable government | Good Governance | 12 x monthly reports on complaints received by 30 June 2019 | Office of the Municipal Manager | Report on complaints received | Output | 12 x monthly reports on complaints received by 30 June 2018 | N/A | 3x monthly reports by 30 September 2018 | 3x monthly reports by 31 December 2018 | 3x monthly reports by 31 March 2019 | 3x monthly reports by 30 June 2019

## Technical
Department – Technical
| KPA | Overall development of the municpality.
| Developmental Objective | To Strengthen good Governace at local level
Vote: Technical Services Department
KPI Number | INDICATOR | Baseline | Vote Indicators | Qtr 1 Target | Qtr 2 Target | Qtr 3 Target | Qtr 4 Target | Annual Target | PI | Action Owner
1 | Provide clean piped water to formal residential properties which are connected to the municipal water infrastructure network as at 30 June 2019 |  |  | N/A | N/A | N/A | Provide clean piped water to formal residential properties which are connected to the municipal water infrastructure network as at 30 June 2019 | Provide clean piped water to formal residential properties which are connected to the municipal water infrastructure network as at 30 June 2019 |  | Technical Services Manager
| Provide electricity to formal residential properties connected to the municipal electrical infrastructure network for both credit and prepaid electrical metering as at 30 June 2019 |  |  | N/A | N/A | N/A | Provide electricity to formal residential properties connected to the municipal electrical infrastructure network for both credit and prepaid electrical metering as at 30 June 2019 | Provide electricity to formal residential properties connected to the municipal electrical infrastructure network for both credit and prepaid electrical metering as at 30 June 2019 |  | Technical Services Manager
| Provide sanitation services to residential properties which are connected to the municipal waste water (sanitation/sewerage) network as at 30 June 2019 |  |  | N/A | N/A | N/A | Provide sanitation services to residential properties which are connected to the municipal waste water (sanitation/sewerage) network as at 30 June 2019 | Provide sanitation services to residential properties which are connected to the municipal waste water (sanitation/sewerage) network as at 30 June 2019 |  | Technical Services Manager
| Provision of refuse removal, refuse dumps and solid waste disposal to all residential account holders as at 30 June 2019 |  |  | N/A | N/A | N/A | Provision of refuse removal, refuse dumps and solid waste disposal to all residential account holders as at 30 June 2019 | Provision of refuse removal, refuse dumps and solid waste disposal to all residential account holders as at 30 June 2019 |  | Technical Services Manager
| Provision of refuse removal, refuse dumps and solid waste disposal to all residential account holders as at 30 June 2019 |  |  | 13 Collection of waste per ward by 30 September 2018 | 13 Collection of waste per ward by 31 December 2018 | 13 Collection of waste per ward by 31 March 2019 | 13 Collection of waste per ward by 30 June 2019 | 52 x free collection per ward of basic refuse removal, refuse dumps and solid waste disposal to registered indigent account holders as at 30 June 2019 |  | Waste Supervisor
| Provision of refuse removal, refuse dumps and solid waste disposal to all residential account holders as at 30 June 2019 |  |  | N/A | N/A | N/A | Provision of refuse removal, refuse dumps and solid waste disposal to all residential account holders as at 30 June 2019 | Provision of refuse removal, refuse dumps and solid waste disposal to all residential account holders as at 30 June 2019 |  | Technical Services Manager
| Refurbishment of Water Service Infrastructure phase 4 by 30 June 2019 |  |  | 25% implementation of project by 30 September 2018 | 50% implementation of the project by 31 December 2018 | 75% implementation of project by 31 March 2019 | 100% implementation of project by 30 June 2019 | Refurbishment of Water Service Infrastructure by phase 4 by 30 June 2019 |  | Technical Services Manager
| To ensure the provision of sustainable basic service to our communities |  |  | 50% implementation of project by 30 September 2018 | 100% implementation of project 31 December 2018 | N/A | N/A | Upgrading of the existing sewage purification works by 30 December 2018 |  | Technical Services Manager
| To ensure the provision of sustainable basic service to our communities |  |  | 25% implementation of project by 30 September 2018 | 50% implementation of the project by 31 December 2018 | 75% implementation of project by 31 March 2019 | 100% implementation of project by 30 June 2019 | Numbering of cemeteries by 30 June 2019 |  | Technical Services Manager
| Closure of existing landfill site and establishment of new Danielskuil Waste Site by 30 June 2019 |  |  | 25% implementation of project by 30 September 2018 | 50% implementation of the project by 31 December 2018 | 75% implementation of project by 31 March 2019 | 100% implementation of project by 30 June 2019 | Closure of existing landfill site and establishment of new Danielskuil Waste Site by 30 June 2019 |  | Technical Services Manager
| Upgrading and Refurbishment of the existing Electrical Main Sub-station by 30 June 2019 |  |  | 25% implementation of project by 30 September 2018 | 50% implementation of the project by 31 December 2018 | 75% implementation of project by 31 March 2019 | 100% implementation of project by 30 June 2019 | Upgrading and Refurbishment of the existing Electrical Main Sub-station by 30 June 2019 |  | Technical Services Manager
| To ensure the provision of sustainable basic service to our communities |  |  | 25% implementation of project by 30 September 2018 | 50% implementation of the project by 31 December 2018 | 75% implementation of project by 31 March 2019 | 100% implementation of project by 30 June 2019 | Replacement of 60 electrical poles by 30 June 2019 |  | Technical Services Manager
| Conversion of 122 Indigent conventional water meters to pre-paid water meters by 30 June 2019 |  |  | 25% implementation of project by 30 September 2018 | 50% implementation of the project by 31 December 2018 | 75% implementation of project by 31 March 2019 | 100% implementation of project by 30 June 2019 | Conversion of 122 Indigent conventional water meters to pre-paid water meters by 30 June 2019 |  | Technical Services Manager
6 | Environmental awareness workshop on caring for the environment |  |  | 1 Environmental awareness workshop held by 30 September 2018 | 1 Environmental awareness workshop held by 30 December 2018 | 1 Environmental awareness workshop held by 31 March 2019 | 1 Environmental awareness workshop held by 30 June 2019 | 4 Environmental awareness workshop held by 30 June 2018 |  | Waste Supervisor
7 | Promoting the collection of waste |  |  | N/A | N/A | N/A | Facilitate one recycling activity by 30 June 2019 | Facilitate one recycling activity by 30 June 2019 |  | Waste Supervisor
59 | Quarterly assessment of municipal facilities/building that needs maintenance |  |  | Assessment of municipal facilities/building that needs maintenance by 30 September 2016 | Assessment of municipal facilities/building that needs maintenance by 31 December 2016 | Assessment of municipal facilities/building that needs maintenance by 31 March 2017 | Assessment of municipal facilities/building that needs maintenance by 31 March 2017 | 4 Quarterly assessment of municipal facilities/building that needs maintenance by 30 June 2017 |  | Technical Services Manager
62 | Quarterly Sitting of Departmental Meetings |  |  | 1 Quarterly Technical Services meeting for each department by 30 September 2018 | 1 Quarterly Technical Services department meeting for each department by 31 December 2019 | 1 Quarterly Technical Services department meeting by 31 March 2019 | 1 Quarterly Technical Services Departent meeting by 30 June 2019 | 4 Quarterly Technical Services departement meetings for each department by 30 June 2019 |  | Technical Services Manager
66 | Monthly sitting of Technical Comittee by 30 June 2017 |  |  | 2 Monthly sittings of Technical Comittee by 30 September 2018 | 3 Monthly sittings of Technical Comittee by 31 December 2018 | 3 Monthly sittings of Technical Comittee by 31 March 2019 | 2 Monthly sittings of Technical Comittee by 30 June 2019 | 10 Monthly sittings of Technical Comittee by 30 June 2019 |  | Technical Services Manager
| Review of the Land Use Management Scheme by 30 June 2019 |  |  | N/A | N/A | N/A | Reviewed of the Land Use Management Scheme by 30 June 2019 | Review of the Land Use Management Scheme by 30 June 2019
TOTAL = | Development of Informal Settlement Relocation and Upgrading Strategy and Policy by 30 June 2018 |  |  | N/A | N/A | N/A | Developed of Informal Settlement Relocation and Upgrading Strategy and Policy by 30 June 2018 | Development of Informal Settlement Relocation and Upgrading Strategy and Policy by 30 June 2018
| Consolidation, subdivision, rezoning and conveyancing for the rectification of stands allocation by 30 June 2019 |  |  | N/A | N/A | N/A | Consolidated subdivision, rezoning and conveyancing for the rectification of stands allocation by 30 June 2019 | Consolidation, subdivision, rezoning and conveyancing for the rectification of stands allocation by 30 June 2019

## Office of the MM
Office of the Municipal Manager
| KPA: | Overall development of the municpality.
| Developmental Objective | To Strengthen good Governace at local level
Vote: Office of the Municipal Manager (1020)
KPI Number | INDICATOR | Baseline | Annual Target | Qtr 1 Target | Qtr 2 Target | Qtr 3 Target | Qtr 4 Target | Annual Target | PI | Action Owner
20 | Temporary jobs creation | 2017/2018 programme completed | 10 temporary jobs created through projects by 30 June 2019 | 1 Database of unemployed youth by 30 September 2018 | 50% Temporary job Created by 30 December 2018 | 75% Temporary jobs Created by 31 March 2019 | 100% Temporary Jobs Created by 30 June 2019 | 10 temporary jobs created through projects by 30 June 2019 |  | Municipal Manager
21 | Conclusion/Update of MoU with the mining companies | 2017/2018 opdated MOU |  | N/A | Updated MoU by 31 December 2018 | N/A | N/A | Updated MoU by 31 December 2018 |  | IDP/LED Officer
22 | 1x Local Economic Developement Plan | 2017/2018 Economic development plan |  | N/A | N/A | N/A | 1x Reviewed Local Economic Development plan by 30 June 2019. | N/A |  | IDP/LED Officer
11 | Sustainable Economic Development | N/A |  | N/A | N/A | N/A | Provision of Trading space for SMMEs by 30 June 2019. | Provision of Trading space for SMMEs by 30 June 2019. |  | IDP/LED Officer
14 | Local Contractors Development | 2017/2018 programme completed |  | 1 developed local contractor by 30 September 2018 | 1 developed local contractor by 31 december 2018 | 1 developed local contractor by 31 March 2019 | 1 developed local contractor by 31 March 2019 | Development of 4 small local emerging suppliers by 30 June 2019 |  | IDP/LED Officer
15 | Development of a database of local businesses/suppliers | N/A |  | N/A | Development of Database of all businesses by 30 June 2019 | N/A | N/A | Development of Database of all businesses by 30 June 2019 |  | IDP/LED Officer
16 | Support one local tourism initiative | N/A |  | N/A | N/A | N/A | Formulation of information brochures to enhance tourism in the area by 30 June 2019 | Formulation of information brochures to enhance tourism in the area by 30 June 2019 |  | IDP/LED Officer
| Support local youth . | N/A |  | N/A | N/A | N/A | 1 Career Exhibition by 30 June 2019 | 1 Career Exhibition by 30 June 2019
51 | Sitting of staff meetings | 2017/2018 programme completed |  | 1 staff meeting held by 30 September 2018 | N/A | 1 staff meeting held by 31 March 2019 | 1 staff meeting held by 30 June 2019 | 3 staff meetings held by 30 June 2019 |  | Municipal Manager
52 | Quarterly sitting of extended management meeting | 2017/2018 programme completed |  | 1 sitting of extended management meeting by 30 September 2018 | 1 sitting of extended management meeting by 31 December 2018 | 1 sitting of extended management meeting by 31 March 2019 | 1 sitting of extended management meeting by 31 June 2019 | 4 sitting of extended management meeting by 30 June 2019 |  | Municipal Manager
53 | Formulation of performance plans | 2017/2018 performance plans |  | 17 performance plans for Unit heads and Managers by July 1 2018 | N/A | N/A | N/A | 17 performance plans for Unit heads and Managers by July 1 2018 |  | PMS Officer
54 | Tabling of mid-year s72 report | report submited |  | N/A | N/A | 1 S72 report per annum by 25 January 2018 | N/A | 1 S72 report per annum by 25 January 2018 |  | PMS Officer
56 | No of performance assessment conducted | 2017/2018 4 performance assessments |  | 1 Quarterly Performance Assessments by 15 October 2018 | 1 Quarterly Performance Assessment by 15 January 2019 | 1 Quarterly Performance Assessment by 15 April 2019 | 1 Quarterly Performance Assessment by 15 July 2019 | 4 Quarterly Performance Assessments by 15 July 2019 |  | PMS Officer
60 | No of Council meetings | 2017/2018 4 x Quarterly Council meetings held |  | 1X Council meetings held by 31 October 2018 | 1x Council meeting held by 31 January 2019 | 1x Council meeting held by 31 April 2019 | 1x Council meeting held by 30 July 2019 | 4 x Quarterly Council meetings held by 31 July 2019 |  | Municipal Manager
61 | 10 Special Council meetings | 2017/2018 10 Special Council Meetings held. |  | 3 Special Council meeting by 31 August 2018 | 2 Special Councils meeting by 31 December 2018 | 3 Special Council meeting by 31 arch 2019 | Special Council meeting by 30 June 2019 | 10 Special Council Meetings by 30 June 2019. |  | Municipal Manager
68 | Quarterly sitting of Audit committee. | 2017/2018 4 meetings held |  | 1 Audit Committee meeting by 30 September 2018. | 1 Audit Committee meeting by 31 December 2018. | 1 Audit Committee meeting by 31 March 2019. | 1 Audit Committee meeting by 30 June 2019. | 4 meetings by 30 June 2019 |  | Internal Audit
69 | sittings of special audit committee meeting by | 2017/2018 sitting of special audit committee held |  | 1 sittings of special audit committee meeting by 31 August 2018 | 1 sittings of special audit committee meeting by 30 November 2018 | N/A | N/A | 2 sittings of special audit committee meeting by 31 November 2019 |  | Internal Audit
70 | Compilation of operational audit plan and review of strategic plan and policies | 2017/2018 completed Audits |  | Compilation of operational audit plan and review of strategic plan and policies by 30 June 2019 | N/A | N/A | N/A | Compilation of operational audit plan and review of strategic plan and policies by 30 June 2019 |  | Internal Audit
71 | Reports to Management on audits performed - Quarterly | 2017/2018 daft report submited |  | Submission of draft report within 7 days after completion of the audit. | Submission of draft report within 7 days after completion of the audit. | Submission of draft report within 7 days after completion of the audit. | Submission of draft report within 7 days after completion of the audit. | Submission of draft report within 7 days after completion of the audit. |  | Internal Audit
72 | Monthly report on progress of AGSA Action Plan and recommendations made by IA | 2017/2018 12 reports reports |  | 3 Monthly reports on progress of AGSA Action Plan and recommendations made by IA by 30 September 2018 | 3 Monthly reports on progress of AGSA Action Plan and recommendations made by IA by 31 December 2018 | 3 Monthly reports on progress of AGSA Action Plan and recommendations made by IA by 31 March 2019 | 3 Monthly reports on progress of AGSA Action Plan and recommendations made by IA by 30 June 2019 | 12 Monthly reports on progress of AGSA Action Plan and recommendations made by IA by 30 June 2019 |  | Internal Audit
73 | Bi-weekly meetings per quarter with management on the implementation of Audit Action |  |  | 6 bi-weekly meetings per quarter with management on the implementation of Audit Action by 30 September 2016 | 6 bi-weekly meetings per quarter with management on the implementation of Audit Action by 31 December 2016 | 6 bi-weekly meetings per quarter with management on the implementation of Audit Action by 31 March 2017 | 6 bi-weekly meetings per quarter with management on the implementation of Audit Action by 31 May 2017 | 24 bi-weekly meetings per quarter with management on the implementation of Audit Action by 30 June 2017 |  | Internal Audit
75 | Risk Assessment conducted quarterly | 2017/2018 risk assessments completed. |  | 1 Risk Assessment conducted by 30 September 2018 | 1 Risk Assessment conducted by 31 December 2018 | 1 Risk Assessment conducted by 31 March 2019 | 1 Risk Assessment conducted by 30 June 2019 | 4 Risk Assessments conducted by 30 June 2019 |  | Risk Officer
76 | Quarterly Submission of Risk Management Reports(4 per department) | 2017/2018 16 Submited risk reports |  | 4 (1 per department) Risk Management Reports submitted by 30 September 2018 | 4 (1 per department) Risk Management Reports submitted by 31 December 2018 | 4 (1 per department) Risk Management Reports submitted by 31 March 2019 | 4 (1 per department) Risk Management Reports submitted by 30 June 2019 | Submission of 16 (4 per department) Risk Management Reports(4 per department) by 30 June 2019 |  | Risk Officer
77 | Adopted IDP Process Plan by Council | 2017/2018 process plan |  | 1x Process Plan by 31 August 2018 | N/A | N/A | N/A | 1x Process Plan by 31 August 2018 |  | IDP/LED Officer
78 | 2 ward IDP/Budget consultative meetings per ward | 2017/2018 programme completed |  | 4 (1 per ward) ward based consultative meeting by 30 September 2018 | N/A | N/A | 4 (1per ward) ward based consultative meeting by 31 March 2019 | 8 (2 per ward) ward IDP/Budget consultative meetings by 30 June 2019 |  | IDP/LED Officer
82 | Draft IDP completed/reviewed and adopted | 2017/2018 IDP |  | N/A | N/A | 1 draft IDP approved by 31 March 2019 | N/A | 1 draft IDP approved by 31 March 2019 |  | IDP/LED Officer
83 | Final IDP completed/reviewed and adopted | 2017/2018 IDP |  | N/A | N/A | N/A | 1 Final IDP approved by 31 May 2019 | 1 Final IDP approved by 31 May 2019 |  | IDP/LED Officer
84 | IDP Rep Forum meetings held - quarterly | IDP REP FORUM |  | 1x IDP Rep Forum meetings held by 30 September 20185 | 1x IDP Rep Forum meetings held by 31 December 2018 | 1x IDP Rep Forum meetings held by 31 March 2019 | 1x IDP Rep Forum meetings held by 30 June 2017 | 4 IDP Rep Forum meetings held by 30 June 2017 |  | IDP/LED Officer
85 | IDP Steering Committee held - Quarterly | 4 IDP steering committee |  | 1x IDP Steering Committee held 30 September 2018 | 1x IDP Steering Committee held 31 December 2018 | 1x IDP Steering Committee held 31 March 2019 | 1x IDP Steering Committee held 30 June 2019 | 4 IDP Steering Committee held by 30 June 2019 |  | IDP/LED Officer
88 | Submission of Draft Annual Report | 2016/2017 Draft Annual report |  | Submission of Draft Annual Report by 31 August 2018 | N/A | N/A | N/A | Submission of Draft Annual Report by 31 August 2018 |  | PMS Officer
89 | Submission of Annual Report before the legislative deadline | 1 Annual report |  | N/A | N/A | 1 x Annual Report submitted by 31 March 2019 | N/A | 1 x Annual Report submitted by 31 March 2019 |  | PMS Officer
TOTAL =

## Office of the mayor
Department – Office of the Mayor
| KPA | Overall development of the municpality.
| Developmental Objective | To Strengthen good Governace at local level
Vote: Office of the Mayor
KPI Number | INDICATOR | Baseline | Vote Indicators | Qtr 1 Target | Qtr 2 Target | Qtr 3 Target | Qtr 4 Target | Annual Target | PI | Action Owner
63 | 10 monthly sittings of Finance Comittee by 30 June 2019 | 2017/2018 FY |  | 2 monthly sittings of Finance Comittee by 30 September 2018 | 3 monthly sittings of Finance Comittee by 31 December 2018 | 3 monthly sittings of Finance Comittee by 31 March 2019 | 2 monthly sittings of Finance Comittee by 30 June 2019 | 10 monthly sittings of Finance Comittee by 30 June 2019 |  | Office of the Mayor
64 | Quarterly sitting of MPAC Comittee | 2017/2018 FY |  | 1 Quarterly sitting of MPAC Comittee by 30 September 2018 | 1 Quarterly sitting of MPAC Comittee by 31 December 2018 | 1 Quarterly sitting of MPAC Comittee by 31 March 2019 | 1 Quarterly sitting of MPAC Comittee by 30 June 2019 | 4 Quarterly sitting of MPAC Comittee by 30 June 2019 |  | Office of the Mayor
65 | Quarterly sitting of Institutional Comittee | 2017/2018 FY |  | 1 Quarterly sitting of Institutional Comittee by 30 September 2018 | 1 Quarterly sitting of Institutional Comittee by 31 December 2018 | 1 Quarterly sitting of Institutional Comittee by 31 March 2019 | 1 Quarterly sitting of Institutional Comittee by 30 June 2019 | 4 Quarterly sittings of Institutional Comittee by 30 June 2019 |  | Office of the Mayor
66 | 10 monthly sittings of Technical Comittee | 2017/2018 FY |  | 2 monthly sittings of Technical Comittee by 30 September 2018 | 3 monthly sittings of Technical Comittee by 31 December 2018 | 3 monthly sittings of Technical Comittee by 31 March 2019 | 2 monthly sittings of Technical Comittee by 30 June 2019 | 10 monthly sittings of Technical Comittee by 30 June 2019 |  | Office of the Mayor
67 | Quarterly sitting of Commonage Comittee | 2017/2018 FY |  | 1 Quarterly sittings of Commonage Comittee by 30 September 2018 | 1 Quarterly sittings of Commonage Comittee by 31 December 2018 | 1 Quarterly sittings of Commonage Comittee by 31 March 2019 | 1 Quarterly sittings of Commonage Comittee by 30 June 2019 | 4 Quarterly sittings of Commonage Comittee by 30 June 2019 |  | Office of the Mayor
79 | Ward committee meetings for each ward = 10 in the financial year | 2017/2018 FY |  | 3 ward committee meetings for each ward by 30 September 2018 | 2 ward committee meetings for each by 31 December 2018 | 3 ward committee meetings for each ward by 31 March 2019 | 2 ward committee meetings for each ward by 30 June 2019 | 10 ward commitee meetings for each ward by 30 June 2019 |  | Office of the Mayor
80 | Ward Meetings | 2017/2018 FY |  | 3 ward meetings for each by 30 September 2018 | 2 ward meetings for each ward by 31 December 2018 | 3 ward meetings for each ward by 31 March 2019 | 2 ward meetings for each by 30 June 2019 | 10 Ward meetings for each ward by 30 June 2019 |  | Office of the Mayor
81 | HIV/AIDS – Mayoral Forum - quarterly |  |  | 1x HIV/AIDS – Mayoral Forum by 30 September 2016 | 1x HIV/AIDS – Mayoral Forum by 31 December 2016 | 1x HIV/AIDS – Mayoral Forum by 31 March 2017 | 1x HIV/AIDS – Mayoral Forum by 30 June 2017 | 4 HIV/AIDS Mayoral Forums by 30 June 2017
TOTAL = 8

## Finance
Department – Finance
| KPA | Overall Finacial Management.
| Developmental Objective | To Strengthen good Governace at local level
Vote: Finance (1050)
KPI Number | INDICATOR | Baseline | Qtr 1 Target | Qtr 2 Target | Qtr 3 Target | Qtr 4 Target | Annual Target | PI | Action Owner
17 | 60% Percentage of operating budget revenue raised/received by 30 June 2019 |  | 15% of Total Operating budget received/raised by 30 September 2018 | 30% of Total Operating budget received/raised by 31 December 2018 | 45% of Total Operating budget received/raised by 31 March 2019 | 60% of Total Operating budget received/raised by 30 June 2019 | 60% of Total Operating budget received/raised by 30 June 2019 |  | Accountant Income
18 | 100% of total Capital Grant funding received by 30 June 2019 |  | N/A | N/A | N/A | 100% of total Capital Grant funding received by 30 June 2019 | 100% of total Capital Grant funding received by 30 June 2019 |  | Accountant BTO
19 | 1 222 indigent households registered by 30 June 2019 |  | 1 222 indigent households registered by 30 June 2019 | N/A | N/A | N/A | 1 222 indigent households registered by 30 June 2019 |  | Accountant Income
20 | 60% of Total Operating Budget Expenditure spent on income received by 30 June 2019 |  | N/A | N/A | N/A | 60% of Total Operating Expenditure spent on income received by 30 June 2019 | 60% of Total Operating Budget Expenditure spent on income received by 30 June 2019 |  | Accountant Expenditure
21 | 95% of Capital budget spent by 30 June 2019 |  | 25% of Capital budget spent by 30 September 2018 | 50% of Capital budget spent by 31 December 2018 | 75% of Capital budget spent by 31 March 2019 | 95% of Capital budget spent by 30 June 2019 | 95% of Capital budget spent by 30 June 2019 |  | Accountant BTO
22 | Compilation of a GRAP compliant asset register by 30 june 2019 |  | GRAP compliant asset register by 31 August 2019 | N/A | N/A | N/A | GRAP compliant asset register by 31 August 2019 |  | Accountant Assets
25 | 4 Quarterly Updates of the Asset Register by 30 June 2019 |  | Quarterly Update of Asset Register by 30 September 2018 | 1 Quarterly Update of Asset Register by 31 December 2018 | 1 Quarterly Update of Asset Register by 31 March 2019 | 1 Quarterly Update of Asset Register by 30 June 2019 | 4 Quarterly Updates of the Asset Register by 30 June 2019 |  | Accountant Assets
26 | 4 quarterly undertakings of inventory of stores by 30 June 2019 |  | 1 quarterly undertaking of inventory of stores by 30 September 2018 | 1 quarterly undertaking of inventory of stores by 31 December 2018 | 1 quarterly undertaking of inventory of stores by 31 March 20179 | 1 quarterly undertaking of inventory of stores by 30 June 2019 | 4 quarterly undertakings of inventory of stores by 30 June 2019 |  | Accountant Assets
27 | Report on list of assests that need to be disposed by 30 June 2019 |  | N/A | N/A | Report on list of assests that need to be disposed by 31 January 2019 | N/A | Report on list of assests that need to be disposed by 31 January 2019 |  | Accountant Assets
28 | 1XDisclosure note in AFS by 31 August 2018 |  | 1XDisclosure note in AFS by 31 August 2018 | N/A | N/A | N/A | 1XDisclosure note in AFS by 31 August 2018 |  | Chief Financial Officer
29 | Formulating of procurement plan by 30 June 2019 |  | Formulating of procurement plan by 30 June 2018 | N/A | N/A | N/A | Formulating of procurement plan by 30 June 2018 |  | Accountant SCM
30 | Review of procurement plan by 25 January 2019
31 | 100% Compliance with the procurement plan by the 30 June 2019 |  | 25% implementation of Procurement Plan by 30 September 2018 | 50% implementation of Procurement Plan by 31 December 2018 | 75% implementation of Procurement Plan by 31 March 2019 | 75% implementation of Procurement Plan by 30 June 2019 | 100% Compliance with the procurement plan by the 30 June 2019 |  | Accountant SCM
32 | Annual Financial Statements submitted by 31 August 2018 |  | 1 AFS per annum submitted by 31 August 2018 | N/A | N/A | N/A | 1 AFS per annum submitted by 31 August 2018 |  | Chief Financial Officer
33 | Submission of Draft Budget by 31 March 2019 |  | N/A | N/A | Submission of Draft Budget 31 March 2019 | N/A | Submission of Draft Budget 31 March 2019. |  | Chief Financial Officer
34 | Submission of Final Budget by 31 May 2019 |  | N/A | N/A | N/A | Submission of Final Budget by 31 May 2019 | Submission of Final Budget by 31 May 2019 |  | Chief Financial Officer
35 | Adjustment budget submitted to Council by 25 January 2019 |  | N/A | N/A | Adjustment budget submitted to Council by 25 Jan 2019 | N/A | Adjustment budget submitted to Council by 25 Jan 2019 |  | Chief Financial Officer
36 | 12 Section 71 reports submitted by the 10th of each month by 31 July 2019 |  | 3X Section 71 Reports submitted by 10 October 2018 | 3 X Section 71 Reports submitted by 10 January 2019 | 3X Section 71 Reports subbmitted by 10 April 2019 | 3X Section 71 Reports submitted by 10 July 2019 | 12 X Section 71 Reports by 10th July 2019 |  | Accountant BTO
37 | 4x Section 52 report submitted quarterly by 31 July 2019 |  | Section 52 report submitted by end of 31 October 2018 | Section 52 report submitted by 31 Januray 2019 | Section 52 report submitted by 31 April 2019 | Section 52 report submitted by 31 July 2019 | 4 Section 52 report submitted quarterly by 31 July 2019 |  | Accountant BTO
38 | Section 72 Report submitted by 25 January 2019 |  | N/A | N/A | Section 72 Report submitted once a year by 31 January 2019 | N/A | Section 72 Report submitted once a year by 31 January 2019 |  | Accountant BTO
62 | 4 quarterly sitting of departmental meetings by 30 June 2019 |  | 1 quarterly sitting of departmental meetings by 30 September 2018 | 1 quarterly sitting of departmental meetings by 31 December 2018 | 1 quarterly sitting of departmental meetings by 31 January 2019 | 1 quarterly sitting of departmental meetings by 30 June 2019 | 4 quarterly sitting of departmental meetings by 30 June 2019 |  | Chief Financial Officer
63 | 10 Monthly sitting of Finance Comittee by 30 June 2019 |  | 2 Monthly sittings of Finance Comittee by 30 September 2018 | 3 Monthly sittings of Finance Comittee by 31 December 2018 | 3 Monthly sittings of Finance Comittee by 31 March 2019 | 2 Monthly sittings of Finance Comittee by 30 June 2097 | 10 Monthly sittings of Finance Comittee by 30 June 2019 |  | Chief Financial Officer
86 | Approval of Draft SDBIP 14 days after approval of Final Budget |  | N/A | N/A | N/A | Approval of Draft SDBIP by 14 June 2018 | Approval of Draft SDBIP by 14 June 2018 |  | Chief Financial Officer
87 | Approved final SDBIP by 30 June 2018 |  | N/A | N/A | N/A | Approved SDBIP by 30 June 2018 | Approved SDBIP by 30 June 2018 |  | Chief Financial Officer/ PMS Officer
90 | Satisfaction assessment conducted |  | N/A | N/A | N/A | 1 x Annual Customer satisfaction assessment 30 June 2019 | 1 x Annual Customer satisfaction assessment 30 June 2019 |  | Accountant Income
91 | 12 monthly Reports on complaints received y 30 June 2019 |  | 3x monthly reports by 30 September 2018 | 3x monthly reports by 31 December 2018 | 3x monthly reports by 31 March 2019 | 3x monthly reports by 30 June 2019 | Monthly report = 12 x monthly reports on complaints received by 30 June 2019 |  | Accountant Income
TOTAL = 29

## Corporate
Department – Corporate Service
| KPA | Overall development of the municpality.
| Developmental Objective | To Strengthen good Governace at local level
Vote: Corporate Services Department
KPI Number | INDICATOR | Baseline | Qtr 1 Target | Qtr 2 Target | Qtr 3 Target | Qtr 4 Target | Annual Target | PI | Action Owner
39 | Filling of budgeted key vacancies within the approved budget by 31 October 2019 |  | N/A | Filling of budgeted key vacancies within the approved budget by 31 October 2018 | N/A | N/A | Filling of budgeted key vacancies within the approved budget by 31 October 2018 |  | HR Officer
40 | Formulation of job description for budgeted vacancies by 30 September 2016 |  | Formulation of job description for budgeted vacancies by 30 September 2018 | N/A | N/A | N/A | Formulation of job description for budgeted vacancies by 30 September 2018 |  | HR Officer
41 | Develop/Review an employment equity plan by 31 August 2016 |  | Develop/Review an employment equity plan by 31 August 2018 | N/A | N/A | N/A | Develop/Review an employment equity plan by 31 August 2018 |  | HR Officer
42 | Functionality of training committee, 6 training committee meetings by 30 June 2017 |  | 2 meetings by 30 September 2018 | 1 meeting by 31 December 2018 | 2 meetings by 31 March 2019 | 1 meeting by 30 June 2019 | 6 meetings in the by 30 June 2019 |  | SDF
| Development of a Workskills Plan by 30 April 2019 |  | N/A | N/A | N/A | 100% Developed Workskills plan by 30 April 2019 | Development of a Workskills Plan by 30 April 2019 |  | SDF
41 | 92% expenditure of Actual budget spent on the implementation of the workplace skills plan |  | 23% of the allocatd worskills plan budget to be spent by 30 September 2018 | 46% of the allocatd worskills plan budget to be spent by 31 December 2018 | 69% of the allocatd worskills plan budget to be spent by 31 March 2019 | 92% of the allocatd worskills plan budget to be spent by 30 June 2019 | 92% of the allocatd worskills plan budget to be spent by 30 June 2019 |  | SDF
42 | Meeting of the LLF |  | 1 LLF meeting by September 2018 | 1 LLF meeting by December 2018 | 1 LLF meeting by 31 March 2019 | 1 LLF meeting by 30 June 2019 | 4 meetings by 30 June 20179 |  | HR Officer
43 | Resolution on all labour disputes |  | N/A | N/A | N/A | 80% resolution of labour disputes by 30 June 2019 | 80% resolution of labour disputes by 30 June 2019 |  | HR Officer
44 | Induction of newly appointed staff |  | N/A | 100% all newly appointed staff inducted by 30 November 2018 | N/A | N/A | 100% all newly appointed staff inducted by 30 November 2018 |  | HR Officer
45 | Evaluation of newly established posts and updating of existing for re-evaluation |  | Evaluation of newly established posts and updating of existing posts for re-evaluation by 31 January 2018 | N/A | N/A | N/A | Evaluation of newly established posts and updating of existing posts for re-evaluation by 31 January 2018 |  | HR Officer
47 | Health and Safety Committee meeting |  | 1 Health and Safety Committe meeting held by 30 September 2018. | 1 Health and Safety Committe meeting held by 31 December 2018 | 1 Health and Safety Committe meeting held by 31 March 2019. | 1 Health and Safety Committe meeting held by 30 June 2019. | 4 Health and Safety committee meetings by 30 June 2019 |  | HR Officer
48 | Monthly meetings with Health and Safety Reps |  | 3 Monthly meetings with Health and Safety Reps by 30 September 2018 | 3 Monthly meetings with Health and Safety Reps by 31 December 2018 | 3 Monthly meetings with Health and Safety Reps by 31 March 2019 | 3 Monthly meetings with Health and Safety Reps by 30 June 2019 | 12 Monthly meetings with Health and Safety Reps by 30 June 2019 |  | HR Officer
54 | Development/Review of a ICT master plan |  | 1 Plan developed/ Reviewed by 30 June 2019 | N/A | N/A | N/A | 1 Plan developed/ Reviewed by 30 June 2019 |  | IT Officer
56 | Improvement/upgrading of ICT network and hardware for mSCOA |  | ICT network improved/upgraded by 30 September 2018 | N/A | N/A | N/A | ICT network improved/upgraded by 30 September 2018 |  | IT Officer
56 | Improve the ICT Governance structure. Quarterly sitting of IT Comittee by 30 June 2017 |  | 1 Quarterly sitting of IT Comittee by 30 September 2018 | 1 Quarterly sitting of IT Comittee by 31 December 2018 | 1 Quarterly sitting of IT Comittee by 31 March 2019 | 1 Quarterly sitting of IT Comittee by 30 June 2019 | Improve the ICT Governance structure.4 Quarterly sitting of IT Comittee by 30 June 2019 |  | IT Officer
60 | Quarterly Sitting of Corporate Services department Meetings |  | Quarterly Sitting of Corporate Services departent Meetings by 30 September 201 | Quarterly Sitting of Corporate Services department by 31 December 2018 | Quarterly Sitting of Corporate Services department meeting 31 March 2019 | Quarterly Sitting of Corporate services department meeting 30 June 2019 | 4 Quarterly Sitting of Corporate Services department Meetings by 30 June 2019 |  | HR Officer
90 | Capacity building for the responsible personnel for customer relations - training 30 November 2016 |  | N/A | Training by the 30 November 2016 | N/A | N/A | Training by the 30 November 2016 |  | HR Officer
TOTAL = 17